## Slide 1: PC builder web application
Team member:
Kevin Song
Siyuan He
Xu Zhang
Haimiao Yu
Chhanna Gaha
Sichao Liu
Guided By: Professor Henry Wong
Deliverable VII
Team Name: Dice

## Slide 2: Comparison sprint 6 vs 7
Sprint 6
We fix the “update user info” error in SPRINT 5
We completed Admin product management view
List Product
Create product list screen
Display products form
Create Product
Build create product api
Finish the code for create product button
Build Product Edit Page
Create edit button and its page
Code function to load product details
Update Product (fail)
We manage to write code for update product; however, it refuse to give right result. So, our team met 75% commitment
SPRINT 7
The Database issue in SPRINT 6 remaining force the team to finish user management section in advance
We completed Admin’s User management ability with only the edit user function remaining
Code optimization is done so the deployment process can be easier.
Our team met 2/3= 66% of the commitment

## Slide 3: What we plan in SPRINT 8
Story ID | User type | I want be able to … | So that… | type
23b | Admin | I can change user’s info as needed Tasks include: Build API for update users Create edit screen UI | I can list product for sale as a user | epic
24 | Seller | Have a seller page | User can now become seller | story
25 |  | Deploy Website | Website is officially good to use | story

## Slide 4
Story ID | Sprint | User type | I want to be able to… | So that … | type | status
1 | I | Developer | Install development tool | Team can start writing the app |  | 
2 | I | Developer | Design Website Template | Team can plan on HTML, CSS |  | 
3 | I | Developer | Install communication platform | Team members are free to communicate |  | 
4 | II | User/Admin | Have a website | I can view/order items, create profile… | story | done
5 | II | User/Admin | Visualized Product Components | I can display images and their info on website | story | done
6 | II | User/Admin | Have detailed Product Page | I can click on product to check their detail | story | done
7 | II | User | Have Shopping cart | I can check purchased product | story | done
8 | III | User/Admin | Register | I can use my profile to perform such as buying…. | story | done
9 | III | User/Admin | Login/Log out securely | My account is private | story | done
10 | III | User | Display added items on cart icon | I can see number of items in cart | story | done
11 | III | User/Admin | Edit qty of item in both product and check out page | I can freely edit item numbers. | story | done
12 | IV | User | Enter name and shipping address | I can have name and shipping stored in profile | story | done
13 | IV | User | I want to check out and have an order number | I can wait for my order | story | done
14 | IV | Admin | I want to see order placed by customer | I can send order by shipping address | story | done
Product Backlog

## Slide 5
Story ID | Sprint | User type | I want be able to … | So that… | type | status
15 | V | User | Have profile displayed | I can see my profile | story | done
16 | V | User | Update my profile info | I can freely edit profile and save | story | done
17 | V | Admin | List Product | I can see all order in list | story | done
18 | VI | Admin | Create Product | I can create product on website | story | done
19 | VI | Admin | Update Product | I can edit product info on website | story | In work
20 | VII | Admin | Upload Product Image | I don’t have to upload image manually | epic | In work
20 a | VII |  | Define upload router |  | task | In work
20 b | VII |  | Create uploads folder |  | task | In work
20 c | VII |  | Edit code in frontend |  | task | Done
21 | VII | Admin | List Users | I can list users out and check them | story | Done
22 | VII | Admin | Delete Users | I can remove unwanted user | story | Done
23 | VIII | Admin | Edit Users | I can change user’s info as needed | epic | 
23a | VIII |  | Build api for update users |  | task | 
23b | VIII |  | Create edit screen UI |  | task | 
Product Backlog 2

## Slide 6
Story ID | Sprint | User type | I want be able to … | So that… | type | status
24 | VIII | Seller | Have a seller page | I can list product for sale as a user | story | 
25 | VIII | Everyone | Deploy website | Website is good to use | story | 
Product Backlog 3

## Slide 7
ID | Process | Test Case | Description | Status | Expected Result | Actual result
21 | List User | Click on Users Button | Login as admin | Passed | Current user should replace by admin user | Admin user successfully logged in
 |  |  | Move mouse to admin icon and when drop down menu show up, click on User button | Passed | User management page showed up | User List page showed up
 |  |  | Different user types are differentiated | Passed | In admin column, normal user marked as no while admin marked as yes | Normal user can not access user management ability. Normal user marked as no
22 | Delete User | Click on Delete button | The Admin User is specified and can not be delete | passed | Normal user will be removed while pop up shows for admin user prevent it from deletion | Delete for normal user success, admin user will not get delete
20c | Edit code in frontend |  | Patch up files and get ready for the final deploy |  | Some bugs were caught during the process | Several typos and css scaling issue has been fixed
Sprint 7 Test Case

## Slide 8: Technologies we used
React

## Slide 9: Reasons we choice some of the technologies
React is an open-source, front end, JavaScript library for building user interfaces or UI components. The reusable components are good for our project.
MongoDB is a source-available cross-platform document-oriented database program. Classified as a NoSQL database program. We choose it as our database because It is fast and easy to use.
Node.js is primarily used for non-blocking, event-driven servers, due to its single-threaded nature. It’s used for traditional web sites and back-end API services

## Slide 10
Story ID | User type | I want be able to … | So that… | type | status
19 | Admin | Update product | I can edit product info on website | story | Error
20 | Admin | Upload Product Image | I don’t have to upload image manually | epic | In work
20a |  | Define upload router |  | task | In work
20b |  | Create uploads folder |  | task | In work
20c |  | Edit code in frontend |  | task | Done
21 | Admin | List Users | I can List user out and check | story | Done
22 | Admin | Delete Users | I can remove unwanted user | story | Done
Sprint backlog VII

## Slide 11
BURNDOWN CHART

## Slide 12
Project Timeline

## Slide 13: Retrospectives
What went well
-Team coordination
-Timely code completion
What needs improvement
-more frequent number of meetings
-task prioritization
Next step
-We need to properly prioritize tasks so that we are not spending too much time on less important task and run out of time for other more important tasks.

## Slide 14: GitHub link
Thank You
https://github.com/ksong227/CS691TeamDice